## Resources
Org | Name | Role for this Activity | Team | Responsible for
Hansen | Amelia Clarke | Sales | Pursuit / Commercial | Customer relationship, pursuit decision, win strategy, commercial sponsorship, Bid Review and submission.
Hansen | Scott Birchall | Pre-Sales Manager | Pre-Sales | Overall RFx governance, WBS, coordination, response integration, quality, demo oversight and packaging.
Hansen | Ravi Menon | Project Manager | Delivery / PMO | Detailed plan, delivery response, RAID, estimates, review packs, action control and closure.
Hansen | Daniel Patel | Pre-Sales SA | Pre-Sales | Solution definition, technical compliance, clarifications, integrations, demo and defence.
Hansen | Katie Lee | Delivery SA | Delivery | Implementation feasibility, delivery architecture, estimates, migration, testing and cutover.
Hansen | Marta Ortiz | Product Team | Product | Capability evidence, roadmap approval, gap disposition, development estimate and solution/demo engineering support.
Hansen | Anton Novak | Enterprise Architect (EA) | Architecture | Strategic architecture alignment, cross-domain decisions, non-standard design review and risk escalation.
Hansen | Grace Holt | Security | Security | Security, privacy, assurance and security approval.
Hansen | Sam Grant | Managed Service & Support | Operations | Support model, SLAs, operating responsibilities, transition and support costs.
Hansen | Helen Ward | Finance | Finance | Cost models, revenue, margin, financial assumptions and approval inputs.
Hansen | Oliver Reid | Legal | Legal | Terms, declarations, contractual exceptions, data and legal approval.
Hansen | Nina Brooks | Training | Training | Training strategy, deliverables, readiness and training estimates.
Hansen | Tom Fischer | Infra/IT | Infrastructure / IT | Environment architecture, sizing, costing, access and demo/delivery environment support.

## Timeline
WBS No. | Phase / Area | Task / Milestone | Team | Owner | Planned Start | Planned Finish | Duration (working days) | Predecessor(s) | Status | Priority | % Complete | Key Deliverable / Exit Criteria | Dependency / Notes
1 | 4.1 Mobilise | Register the RFx and customer deadlines. | Pre-Sales Manager | Scott Birchall | 2026-10-01 | 2026-10-05 |  |  | Complete | High | 100% | RFx registered and customer deadlines captured
3 | 4.1 Mobilise | Record bid/no-bid status and any conditions. | Pre-Sales Manager | Scott Birchall | 2026-10-02 | 2026-10-06 |  | 1 | Complete | Medium | 100% | Bid/no-bid decision and conditions recorded
13 | 4.4 Mobilise | Issue kick-off pack and arrange kick-off meeting. | Pre-Sales Manager | Scott Birchall | 2026-10-08 | 2026-10-12 |  | 9,11,12 | Complete | Medium | 100% | Kick-off completed; WBS, timeline, gates and working practices agreed
17 | 5.2 Analyse and Clarify | Submit clarification questions to the customer before deadline. | Sales | Amelia Clarke | 2026-10-15 | 2026-10-19 |  | 14,15,16 | In Progress | High | 50% | Prioritised clarification questions submitted
22 | 6.1 Shape Solution, Delivery, Estimates and Demo | Create a high-level solution architecture and summary view. First draft solution. | Pre-Sales SA | Daniel Patel | 2026-10-15 | 2026-10-19 |  | 19 | In Progress | Medium | 50% | First-draft solution architecture available for review
29 | 6.2 Shape Solution, Delivery, Estimates and Demo | Present solution architecture, high-level solution and key estimation drivers. | Project Manager | Ravi Menon | 2026-10-19 | 2026-10-23 |  | 22,25,28 | In Progress | Medium | 50% | Delivery and stakeholders aligned on solution and estimation drivers
39 | 6.3 Shape Solution, Delivery, Estimates and Demo | Review and revise estimates with SMEs. | Project Manager | Ravi Menon | 2026-10-29 | 2026-11-02 |  | 32,33,34,35,36,37,38 | Not Started | Medium | 0% | Scope, effort, contingency and dependencies reconciled
45 | 6.4 Shape Solution, Delivery, Estimates and Demo | Prepare and hold POC kick-off meeting. | Pre-Sales SA | Pre-Sales SA |  |  |  | 42,43,44 | Not Started | Medium | 0% | Use cases, requirements, plan and responsibilities agreed | Only applicable when demo/POC is required
54 | 6.4 Shape Solution, Delivery, Estimates and Demo | Hold the demo or POC. | Pre-Sales SA | Pre-Sales SA |  |  |  | 49,50,51,52,53 | Not Started | Medium | 0% | Demo or POC delivered | Only applicable when demo/POC is required
64 | 7.2 Author Response | Complete the RFP response in the approved framework. | Assigned section owners | Scott Birchall | 2026-10-29 | 2026-11-02 |  | 56,57,58,59,60,62,63 | Not Started | Medium | 0% | All response content completed in approved framework
68 | 7.3 Author Response | Confirm requirements, annexes, proposal and cost model are mutually consistent. | Pre-Sales Manager | Scott Birchall | 2026-10-30 | 2026-11-05 |  | 61,64,65,66,67 | Not Started | Medium | 0% | Response components are complete and mutually consistent
74 | 8.2 Review and Approve | Hold the Service Delivery Review. | Project Manager | Ravi Menon | 2026-11-02 | 2026-11-06 |  | 70,71,72,73 | Not Started | High | 0% | Service Delivery Review completed and decisions recorded
77 | 8.3 Review and Approve | Hold the Bid Review and record the outcome. | Sales | Amelia Clarke | 2026-11-05 | 2026-11-09 |  | 74,75,76 | Not Started | High | 0% | Go, conditional-go or no-go outcome recorded
79 | 8.4 Review and Approve | Request and obtain final approvals from applicable functions. | Sales | Amelia Clarke | 2026-11-06 | 2026-11-10 |  | 77,78 | Not Started | High | 0% | All applicable functional approvals obtained
80 | 8.4 Review and Approve | Freeze the approved response baseline. | Pre-Sales Manager | Scott Birchall | 2026-11-06 | 2026-11-11 |  | 79 | Not Started | High | 0% | Approved response baseline frozen and change-controlled
85 | 9.2 Package and Submit | Issue the proposal to the customer in accordance with customer requirements. | Sales | Amelia Clarke | 2026-11-06 | 2026-11-12 |  | 80,81,82,83,84 | Not Started | High | 0% | Final proposal submitted in accordance with customer requirements
87 | 9.2 Package and Submit | Obtain and retain customer acknowledgement where available. | Sales | Amelia Clarke | 2026-11-09 | 2026-11-13 |  | 85,86 | Not Started | Medium | 0% | Customer acknowledgement retained where available
91 | 10.1 Follow-up, Defence and Close | Prepare and issue the proposal follow-up meeting in accordance with customer requirements. | Pre-Sales Manager | Scott Birchall | 2026-11-20 | 2026-11-26 |  | 88,89,90 | Not Started | High | 0% | Follow-up or defence meeting completed as required
92 | 10.2 Follow-up, Defence and Close | Confirm the outcome and capture customer feedback where available. | Sales | Amelia Clarke | 2026-11-23 | 2026-11-27 |  | 91 | Not Started | Medium | 0% | Outcome and available customer feedback recorded
94 | 10.2 Follow-up, Defence and Close | Close tracking codes, archive the final record and transfer reusable knowledge. | Pre-Sales Manager | Scott Birchall | 2026-11-30 | 2026-12-04 |  | 92,93 | Not Started | Medium | 0% | Opportunity process closed and reusable assets archived
Formulas:
Duration (working days) = IF(OR([Planned Start]="",[Planned Finish]=""),"",MAX(0,NETWORKDAYS([Planned Start],[Planned Finish])-1))

## WBS
No | Type | Area/Document | Name/Description | Team | Owner | Due Date | Status | Prioirty | lead Comment | Additional Comments
1 | Process Activity | 4.1 Mobilise | Register the RFx and customer deadlines. | Pre-Sales Manager | Scott Birchall | 2026-10-05 | Complete | High
2 | Process Activity | 4.1 Mobilise | Confirm scope, submission method, mandatory formats, language, validity period and customer contacts. | Pre-Sales Manager | Scott Birchall | 2026-10-06 | Complete | Medium
3 | Process Activity | 4.1 Mobilise | Record bid/no-bid status and any conditions. | Pre-Sales Manager | Scott Birchall | 2026-10-06 | Complete | Medium
4 | Process Activity | 4.1 Mobilise | Confirm whether a demo or POC is required; remove the workstream if not applicable. (See POC process if applicable) | Pre-Sales Manager | Scott Birchall | 2026-10-07 | Complete | Medium
5 | Process Activity | 4.2 Mobilise | Create the opportunity Teams/SharePoint area and controlled folder structure. | Pre-Sales Manager | Scott Birchall | 2026-10-07 | Complete | Medium
6 | Process Activity | 4.2 Mobilise | Create the tracking Epic/project code and agree time-booking expectations. | Pre-Sales Manager | Scott Birchall | 2026-10-08 | Complete | Medium
7 | Process Activity | 4.2 Mobilise | Load customer documents unchanged and create a document register. | Pre-Sales Manager | Scott Birchall | 2026-10-08 | Complete | Medium
8 | Process Activity | 4.2 Mobilise | Select proposal, compliance, question, review and estimate templates. | Pre-Sales Manager | Scott Birchall | 2026-10-09 | Complete | Medium
9 | Process Activity | 4.3 Mobilise | Break the response into milestones, annexes, requirement groups, proposal sections, solution tasks, estimate tasks, demo tasks and reviews. Create section-level and requirement-level ownership. WBS | Pre-Sales Manager | Scott Birchall | 2026-10-09 | Complete | Medium
10 | Process Activity | 4.3 Mobilise | Setup regular progress meetings to walkthrough WBS | Pre-Sales Manager | Scott Birchall | 2026-10-09 | Complete | Medium
11 | Process Activity | 4.3 Mobilise | Assign team, owner, due date, status and comments to each task. | Pre-Sales Manager | Scott Birchall | 2026-10-09 | Complete | Medium
12 | Process Activity | 4.3 Mobilise | Create the initial RAID log and link known dependencies to relevant tasks. | Project Manager | Ravi Menon | 2026-10-09 | Complete | Medium
13 | Process Activity | 4.4 Mobilise | Issue a kick-off pack covering customer context, scope, solution hypothesis, assumptions, impacted functions, WBS, timeline, review gates and working practices. Arrange Kick Off meeting | Pre-Sales Manager | Scott Birchall | 2026-10-12 | Complete | Medium
14 | Process Activity | 5.1 Analyse and Clarify | Review every customer file and classify it as instruction, requirement, commercial, legal, security, environmental, delivery, reference or definition material. Identify mandatory response cells, attachments, declarations and signatures. | Pre-Sales Manager | Scott Birchall | 2026-10-13 | Complete | Medium
15 | Process Activity | 5.2 Analyse and Clarify | Capture a concise question, source reference, rationale, impact if unanswered and proposed working assumption. Q&A template | Pre-Sales SA | Daniel Patel | 2026-10-15 | Complete | Medium
16 | Process Activity | 5.2 Analyse and Clarify | De-duplicate and prioritise clarification questions before Sales submits them. | Pre-Sales Manager | Scott Birchall | 2026-10-16 | Complete | Medium
17 | Process Activity | 5.2 Analyse and Clarify | Submit clarification questions to the customer before deadline | Sales | Amelia Clarke | 2026-10-19 | In Progress | High
18 | Process Activity | 5.2 Analyse and Clarify | Store received Q&A sheet updates from customer in the shared folder and notify stakeholders | Sales | Amelia Clarke | 2026-10-21 | In Progress | Medium
19 | Process Activity | 5.2 Analyse and Clarify | Track customer responses and update scope, assumptions, RAID and affected response sections. | Project Manager | Ravi Menon | 2026-10-23 | In Progress | Medium
20 | Process Activity | 5.3 Analyse and Clarify | Assign presenters | Pre-Sales Manager | Scott Birchall | 2026-10-23 | In Progress | Medium
21 | Process Activity | 5.3 Analyse and Clarify | Record decisions and translate them into WBS updates, response changes and new dependencies. | Project Manager | Ravi Menon | 2026-10-27 | Not Started | Medium
22 | Process Activity | 6.1 Shape Solution, Delivery, Estimates and Demo | Create a high-level solution architecture and summary view. First draft solution | Pre-Sales SA | Daniel Patel | 2026-10-19 | In Progress | Medium
23 | Process Activity | 6.1 Shape Solution, Delivery, Estimates and Demo | Present first draft solution to wider solution team, key value proposition differentiators, sales messaging | Pre-Sales SA | Daniel Patel | 2026-10-20 | In Progress | Medium
24 | Process Activity | 6.1 Shape Solution, Delivery, Estimates and Demo | Define application scope, integration boundaries, infrastructure needs, non-functional considerations | Pre-Sales SA | Daniel Patel | 2026-10-21 | In Progress | Medium
25 | Process Activity | 6.1 Shape Solution, Delivery, Estimates and Demo | Transformation/implementation approach | Pre-Sales SA, Delivery | Daniel Patel | 2026-10-22 | In Progress | Medium
26 | Process Activity | 6.1 Shape Solution, Delivery, Estimates and Demo | Document assumptions, exclusions and dependencies using customer terminology. | Project Manager | Ravi Menon | 2026-10-23 | In Progress | Medium
27 | Process Activity | 6.2 Shape Solution, Delivery, Estimates and Demo | Define methodology, phases, governance, RACI, change control, environments, testing, migration, cutover, readiness, acceptance and support transition. | Project Manager | Ravi Menon | 2026-10-23 | In Progress | Medium
28 | Process Activity | 6.2 Shape Solution, Delivery, Estimates and Demo | Prepare presentation deck for estimation team + wider stakeholders | Project Manager | Ravi Menon | 2026-10-23 | In Progress | Medium
29 | Process Activity | 6.2 Shape Solution, Delivery, Estimates and Demo | Present solution architecture, high level solution and key estimation drivers to Delivery and wider stakeholders | Project Manager | Ravi Menon | 2026-10-23 | In Progress | Medium
30 | Process Activity | 6.2 Shape Solution, Delivery, Estimates and Demo | Develop the delivery timeline and resource profile. | Project Manager | Ravi Menon | 2026-10-26 | Not Started | Medium
31 | Process Activity | 6.2 Shape Solution, Delivery, Estimates and Demo | Maintain delivery-specific risks, assumptions, issues and dependencies. | Project Manager | Ravi Menon | 2026-10-27 | Not Started | Medium
32 | Process Activity | 6.3 Shape Solution, Delivery, Estimates and Demo | Create ROM/OOM/WBS estimates for implementation activities. | Project Manager | Ravi Menon | 2026-10-27 | Not Started | Medium
33 | Process Activity | 6.3 Shape Solution, Delivery, Estimates and Demo | Create ROM/OOM/WBS estimates for product-development activities. | Project Manager | Ravi Menon | 2026-10-28 | Not Started | Medium
34 | Process Activity | 6.3 Shape Solution, Delivery, Estimates and Demo | Create ROM/OOM/WBS estimates for training activities. | Training | Nina Brooks | 2026-10-29 | Not Started | Medium
35 | Process Activity | 6.3 Shape Solution, Delivery, Estimates and Demo | Create ROM/OOM/WBS estimates for Managed Services & Support & Maintenance | Managed Services & Support | Sam Grant | 2026-10-30 | Not Started | Medium
36 | Process Activity | 6.3 Shape Solution, Delivery, Estimates and Demo | Create ROM/OOM/WBS estimates for infrastructure deployment. | Infra/IT | Tom Fischer | 2026-10-30 | Not Started | Medium
37 | Process Activity | 6.3 Shape Solution, Delivery, Estimates and Demo | Create sizing for the infrastructure solution. | Infra/IT | Tom Fischer | 2026-10-30 | Not Started | Medium
38 | Process Activity | 6.3 Shape Solution, Delivery, Estimates and Demo | Create costings for the infrastructure solution. | Infra/IT | Tom Fischer | 2026-10-30 | Not Started | Medium
39 | Process Activity | 6.3 Shape Solution, Delivery, Estimates and Demo | Review and revise estimates with SMEs, reconciling scope, effort, contingency and dependencies. | Project Manager | Ravi Menon | 2026-11-02 | Not Started | Medium
40 | Process Activity | 6.3 Shape Solution, Delivery, Estimates and Demo | Produce the licence cost model covering cost, revenue and margin. | Sales | Amelia Clarke | 2026-11-03 | Not Started | Medium
41 | Process Activity | 6.3 Shape Solution, Delivery, Estimates and Demo | Produce the maintenance and support cost model covering cost, revenue and margin. | Finance | Helen Ward | 2026-11-04 | Not Started | Medium
56 | Process Activity | 7.1 Author Response | Preserve the customer workbook structure and response conventions. | Pre-Sales Manager | Scott Birchall | 2026-10-27 | Not Started | Medium
57 | Process Activity | 7.1 Author Response | Assign each requirement to the correct functional owner. | Pre-Sales Manager | Scott Birchall | 2026-10-28 | Not Started | Medium
58 | Process Activity | 7.1 Author Response | Draft each assigned compliance response with requirement-specific explanation, evidence, assumptions and exceptions. | Assigned functional owner | Scott Birchall | 2026-10-29 | Not Started | Medium
59 | Process Activity | 7.1 Author Response | Validate product capability, roadmap and product-gap statements. | Product Team | Marta Ortiz | 2026-10-29 | Not Started | Medium
60 | Process Activity | 7.1 Author Response | Validate strategic, cross-domain and non-standard architecture statements. | Enterprise Architect (EA) | Anton Novak | 2026-10-30 | Not Started | Medium
61 | Process Activity | 7.1 Author Response | Run cross-document consistency checks for terminology, scope, hosting, support, security and commercial commitments. | Pre-Sales Manager | Scott Birchall | 2026-10-30 | Not Started | Medium
62 | Process Activity | 7.2 Author Response | Establish the proposal or SOW response framework and template. | Pre-Sales Manager | Scott Birchall | 2026-10-30 | Not Started | Medium
63 | Process Activity | 7.2 Author Response | Create an outcome-led narrative linking customer objectives to the solution, operating model, architecture, delivery, assurance and commercials. | Sales | Amelia Clarke | 2026-10-30 | Not Started | Medium
64 | Process Activity | 7.2 Author Response | Complete the RFP response in the approved framework. | Assigned section owners | Scott Birchall | 2026-11-02 | Not Started | Medium
65 | Process Activity | 7.3 Author Response | Confirm all assigned sections are complete in the approved template. | Assigned section owners | Scott Birchall | 2026-11-03 | Not Started | Medium
66 | Process Activity | 7.3 Author Response | Remove placeholders, unresolved comments and broken references. | Assigned section owners | Scott Birchall | 2026-11-03 | Not Started | Medium
67 | Process Activity | 7.3 Author Response | Confirm all claims are supported by Product Team, EA or specialist evidence as applicable. | Assigned section owners | Scott Birchall | 2026-11-04 | Not Started | Medium
68 | Process Activity | 7.3 Author Response | Confirm requirements, annexes, proposal and cost model are mutually consistent. | Pre-Sales Manager | Scott Birchall | 2026-11-05 | Not Started | Medium
69 | Process Activity | 7.3 Author Response | Make open exceptions visible in the RAID and review packs. | Project Manager | Ravi Menon | 2026-11-06 | Not Started | Medium
70 | Process Activity | 8.1 Review and Approve | Authors self-check completeness and evidence. | Assigned section owner | Scott Birchall | 2026-11-06 | Not Started | Medium
71 | Process Activity | 8.1 Review and Approve | Workstream leads perform technical and narrative reviews. | Pre-Sales SA | Daniel Patel | 2026-11-06 | Not Started | Medium
72 | Process Activity | 8.1 Review and Approve | Complete the final internal review and update the cost model and proposal. | Pre-Sales Manager | Scott Birchall | 2026-11-06 | Not Started | Medium
73 | Process Activity | 8.2 Review and Approve | Create the Service Delivery Review pack. | Project Manager | Ravi Menon | 2026-11-06 | Not Started | High
74 | Process Activity | 8.2 Review and Approve | Hold the Service Delivery Review. | Project Manager | Ravi Menon | 2026-11-06 | Not Started | High
75 | Process Activity | 8.2 Review and Approve | Record decisions, owners and due dates and update the proposal and estimates before Bid Review. | Project Manager | Ravi Menon | 2026-11-06 | Not Started | High
76 | Process Activity | 8.3 Review and Approve | Prepare the Bid Review pack. | Sales | Amelia Clarke | 2026-11-09 | Not Started | High
77 | Process Activity | 8.3 Review and Approve | Hold the Bid Review and record the go, conditional-go or no-go outcome. | Sales | Amelia Clarke | 2026-11-09 | Not Started | High
78 | Process Activity | 8.3 Review and Approve | Resolve every Bid Review condition or obtain an explicitly documented waiver. | Named condition owner | Scott Birchall | 2026-11-10 | Not Started | High
79 | Process Activity | 8.4 Review and Approve | Request and obtain final approvals from applicable functions. | Sales | Amelia Clarke | 2026-11-10 | Not Started | High
80 | Process Activity | 8.4 Review and Approve | Freeze the approved response baseline and control all subsequent changes. | Pre-Sales Manager | Scott Birchall | 2026-11-11 | Not Started | High
81 | Process Activity | 9.1 Package and Submit | Create final proposal documents and store them in the final proposal folder. | Pre-Sales Manager | Scott Birchall | 2026-11-11 | Not Started | Medium
82 | Process Activity | 9.1 Package and Submit | Apply customer naming, format, file-size, signature and password or encryption requirements. | Pre-Sales Manager | Scott Birchall | 2026-11-11 | Not Started | Medium
83 | Process Activity | 9.1 Package and Submit | Remove comments, tracked changes, hidden text, draft watermarks and internal-only notes. | Pre-Sales Manager | Scott Birchall | 2026-11-11 | Not Started | Medium
84 | Process Activity | 9.1 Package and Submit | Verify links, contents pages, numbering, attachments and package integrity. | Pre-Sales Manager | Scott Birchall | 2026-11-12 | Not Started | Medium
85 | Process Activity | 9.2 Package and Submit | Issue the proposal to the customer in accordance with customer requirements. | Sales | Amelia Clarke | 2026-11-12 | Not Started | High
86 | Process Activity | 9.2 Package and Submit | Record the submitted files, version, date/time, sender, recipients or portal reference and upload evidence. | Pre-Sales Manager | Scott Birchall | 2026-11-12 | Not Started | Medium
87 | Process Activity | 9.2 Package and Submit | Obtain and retain customer acknowledgement where available. | Sales | Amelia Clarke | 2026-11-13 | Not Started | Medium
88 | Process Activity | 10.1 Follow-up, Defence and Close | Create the proposal follow-up folders in Teams. | Pre-Sales Manager | Scott Birchall | 2026-11-18 | Not Started | Medium
89 | Process Activity | 10.1 Follow-up, Defence and Close | Coordinate proposal follow-up responses. | Pre-Sales Manager | Scott Birchall | 2026-11-20 | Not Started | Medium
90 | Process Activity | 10.1 Follow-up, Defence and Close | Prepare RFP Defence pack | Pre-Sales Manager | Scott Birchall | 2026-11-23 | Not Started | Medium
91 | Process Activity | 10.1 Follow-up, Defence and Close | Prepare and issue the proposal follow-up meeting or in accordance with customer requirements. | Pre-Sales Manager | Scott Birchall | 2026-11-26 | Not Started | High
92 | Process Activity | 10.2 Follow-up, Defence and Close | Confirm the outcome and capture customer feedback where available. | Sales | Amelia Clarke | 2026-11-27 | Not Started | Medium
93 | Process Activity | 10.2 Follow-up, Defence and Close | Hold a retrospective covering process, proposition, solution, commercials, teamwork, tools and reusable assets. | Project Manager | Ravi Menon | 2026-12-01 | Not Started | Medium
94 | Process Activity | 10.2 Follow-up, Defence and Close | Close tracking codes, archive the final record and transfer reusable knowledge to the document library. | Pre-Sales Manager | Scott Birchall | 2026-12-04 | Not Started | Medium
95 | Proposal Volume | Volume 1 | Executive & Solution Proposal | Pre-Sales Manager | Scott Birchall | 2026-10-26 | Not Started | High
96 | Proposal Section | 1 | Executive Summary | Sales | Amelia Clarke | 2026-10-26 | Not Started | Medium
97 | Proposal Section | 2 | Future Lead-to-Order Operating Model | Pre-Sales SA | Daniel Patel | 2026-10-27 | Not Started | Medium
98 | Proposal Section | 3 | Solution Principles | Pre-Sales SA | Daniel Patel | 2026-10-27 | Not Started | Medium
99 | Proposal Section | 4 | Proposed Solution Overview | Pre-Sales SA | Daniel Patel | 2026-10-27 | Not Started | Medium
100 | Proposal Section | 4.1 | Hansen Solution Components | Pre-Sales SA | Daniel Patel | 2026-10-28 | Not Started | Medium
101 | Proposal Section | 4.2 | Solution Alignment to Requirements | Pre-Sales SA | Daniel Patel | 2026-10-28 | Not Started | Medium
102 | Proposal Section | 4.2.1 | Salesforce Integration | Pre-Sales SA | Daniel Patel | 2026-10-28 | Not Started | Medium
103 | Proposal Section | 4.2.2 | Quote Workflow | Pre-Sales SA | Daniel Patel | 2026-10-29 | Not Started | Medium
104 | Proposal Section | 4.2.3 | Configure Price Quote | Pre-Sales SA | Daniel Patel | 2026-10-29 | Not Started | Medium
105 | Proposal Section | 4.2.4 | Price Negotiations & Approvals | Pre-Sales SA | Daniel Patel | 2026-10-30 | Not Started | Medium
106 | Proposal Section | 4.2.5 | Customer Contracts & Commitments | Pre-Sales SA | Daniel Patel | 2026-10-30 | Not Started | Medium
107 | Proposal Section | 4.2.6 | Contract to Order | Pre-Sales SA | Daniel Patel | 2026-10-30 | Not Started | Medium
108 | Proposal Section | 4.2.7 | Order Capture & Submission | Pre-Sales SA | Daniel Patel | 2026-10-30 | Not Started | Medium
109 | Proposal Section | 4.2.8 | Order Decomposition & Fulfilment | Pre-Sales SA | Daniel Patel | 2026-10-30 | Not Started | Medium
110 | Proposal Section | 4.2.9 | Network Planning & Inventory | Pre-Sales SA | Daniel Patel | 2026-10-30 | Not Started | Medium
111 | Proposal Section | 4.2.10 | Operational Visibility & Exception Management | Pre-Sales SA | Daniel Patel | 2026-10-30 | Not Started | Medium
112 | Proposal Section | 4.2.11 | MCP Interface for AI Agents | Product Team | Marta Ortiz | 2026-10-30 | Not Started | Medium
113 | Proposal Section | 4.3 | Integration & Open Architecture | Pre-Sales SA | Daniel Patel | 2026-10-30 | Not Started | Medium
114 | Proposal Section | 5 | Future Growth, Automation and Innovation | Product Team | Marta Ortiz | 2026-11-02 | Not Started | Medium
115 | Proposal Section | 6 | Security, Compliance & Assurance | Security | Grace Holt | 2026-11-02 | Not Started | Medium
116 | Proposal Section | 7 | Customer Success & Support | Managed Service & Support | Sam Grant | 2026-11-03 | Not Started | Medium
117 | Proposal Volume | Volume 2 | Transformation & Delivery Proposal | Project Manager | Ravi Menon | 2026-10-28 | Not Started | High
118 | Proposal Section | 8 | Transformation Roadmap & Phasing | Project Manager | Ravi Menon | 2026-10-29 | Not Started | Medium
119 | Proposal Section | 9 | Delivery Methodology & Execution Model | Project Manager | Ravi Menon | 2026-10-29 | Not Started | Medium
120 | Proposal Section | 10 | Governance Structure | Project Manager | Ravi Menon | 2026-10-30 | Not Started | Medium
121 | Proposal Section | 11 | Roles & Responsibilities / RACI | Project Manager | Ravi Menon | 2026-10-30 | Not Started | Medium
122 | Proposal Section | 12 | Change Control | Project Manager | Ravi Menon | 2026-10-30 | Not Started | Medium
123 | Proposal Section | 13 | Integration Strategy | Pre-Sales SA | Daniel Patel | 2026-10-30 | Not Started | Medium
124 | Proposal Section | 14 | Environment & DevOps Strategy | Infra | Tom Fischer | 2026-10-30 | Not Started | Medium
125 | Proposal Section | 15 | Testing & Quality Assurance | Delivery SA | Katie Lee | 2026-11-02 | Not Started | Medium
126 | Proposal Section | 16 | Data Continuity & Migration | Delivery SA | Katie Lee | 2026-11-03 | Not Started | Medium
127 | Proposal Section | 17 | Cutover & Go-Live | Project Manager | Ravi Menon | 2026-11-03 | Not Started | Medium
128 | Proposal Section | 18 | Business Readiness & Enablement | Training | Nina Brooks | 2026-11-04 | Not Started | Medium
129 | Proposal Section | 19 | Assumptions, Dependencies & Exclusions | Pre-Sales Manager | Scott Birchall | 2026-11-05 | Not Started | Medium
131 | Proposal Volume | Volume 3 | Corporate, Commercial & Compliance | Sales | Amelia Clarke | 2026-10-30 | Not Started | High
132 | Proposal Section | 21 | Hansen Company Profile | Sales | Amelia Clarke | 2026-10-30 | Not Started | Medium
133 | Proposal Section | 22 | References | Sales | Amelia Clarke | 2026-10-30 | Not Started | Medium
134 | Proposal Section | 23 | Commercial Summary | Sales | Amelia Clarke | 2026-10-30 | Not Started | Medium
135 | Proposal Section | 23.1 | Commercial Assumptions | Sales | Amelia Clarke | 2026-10-30 | Not Started | Medium
136 | Proposal Section | 23.2 | Annual Software Licence | Sales | Amelia Clarke | 2026-11-02 | Not Started | Medium
137 | Proposal Section | 23.3 | RGU Growth Tier Structure | Sales | Amelia Clarke | 2026-11-03 | Not Started | Medium
138 | Proposal Section | 23.4 | Renewal Protection and CPI Indexation | Sales | Amelia Clarke | 2026-11-03 | Not Started | Medium
139 | Proposal Section | 23.5 | Commercial Exclusions and Change Control | Sales | Amelia Clarke | 2026-11-04 | Not Started | Medium
140 | Proposal Section | 24 | ESG & Sustainability | Assigned Functional Owner | Scott Birchall | 2026-11-04 | Not Started | Medium
141 | Proposal Section | 25 | Appendix A - Compliance Summary | Pre-Sales Manager | Scott Birchall | 2026-11-05 | Not Started | Medium
142 | Proposal Section | 26 | Appendix B - Environmental Requirement Mapping | Assigned Functional Owner | Scott Birchall | 2026-11-06 | Not Started | Medium

## Demo POC
No | Type | Area/Document | Name/Description | Team | Owner | Due Date | Status | Prioirty | % | lead Comment | Additional Comments
42 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Confirm whether a demo or POC is required; remove the workstream if not applicable. | Pre-Sales Manager | Pre-Sales Manager |  | Not Started | Medium | 0% | Accountable: Pre-Sales Manager | Consulted: Sales; Pre-Sales SA; Product Team; Project Manager; Informed: All other roles
43 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Identify demo or POC use cases. | Pre-Sales SA | Pre-Sales SA |  | Not Started | Medium | 0% | Accountable: Pre-Sales Manager | Consulted: Sales; Product Team; Enterprise Architect (EA); Delivery SA; Project Manager; Informed: All other roles
44 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Define requirements and the demo plan. | Pre-Sales SA | Pre-Sales SA |  | Not Started | Medium | 0% | Accountable: Pre-Sales Manager | Consulted: Product Team; Enterprise Architect (EA); Delivery SA; Project Manager; Infra/IT; Informed: Sales; remaining specialists
45 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Prepare and hold POC Kick off meeting | Pre-Sales SA | Pre-Sales SA |  | Not Started | Medium | 0% | Accountable: Pre-Sales Manager | Consulted: Product Team; Enterprise Architect (EA); Delivery SA; Project Manager;; Informed: Wider Stakeholders
46 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Review demo requirements with the development team. | Pre-Sales SA | Pre-Sales SA; Product Team, Pre-Sales Development Team |  | Not Started | Medium | 0% | Accountable: Pre-Sales Manager | Consulted: Delivery SA; Enterprise Architect (EA); Project Manager; Informed: Sales; remaining specialists
47 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Identify the development work required. | Product Team, Pre-Sales Development Team | Product Team, Pre-Sales Development Team |  | Not Started | Medium | 0% | Accountable: Product Team, Pre-Sales Development Team | Consulted: Pre-Sales SA; Delivery SA; Enterprise Architect (EA); Project Manager; Informed: Sales; Pre-Sales Manager; remaining specialists
48 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Create the required tracked development tasks using the agreed template. | Product Team, Pre-Sales Development Team | Product Team, Pre-Sales Development Team |  | Not Started | Medium | 0% | Accountable: Product Team, Pre-Sales Development Team | Consulted: Pre-Sales SA; Project Manager; Informed: Sales; Pre-Sales Manager; Delivery SA; Enterprise Architect (EA); remaining specialists
49 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Configure and test the required demo use cases. | Product Team | Product Team; Pre-Sales SA; Pre-Sales Development Team |  | Not Started | Medium | 0% | Accountable: Pre-Sales Manager | Consulted: Delivery SA; Enterprise Architect (EA); Project Manager; Informed: Sales; remaining specialists
50 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Review and test the configured use cases with the development team. | Pre-Sales SA | Pre-Sales SA; Product Team; Pre-Sales Development Team |  | Not Started | Medium | 0% | Accountable: Pre-Sales Manager | Consulted: Delivery SA; Enterprise Architect (EA); Infra/IT; Informed: Sales; Project Manager; remaining specialists
51 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Create the demo or POC script and slides. | Pre-Sales SA | Pre-Sales SA |  | Not Started | Medium | 0% | Accountable: Pre-Sales Manager | Consulted: Sales; Product Team; Enterprise Architect (EA); Delivery SA; Informed: Project Manager; Infra/IT; remaining specialists
52 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Book the demo through the agreed internal scheduling process. | Pre-Sales SA | Pre-Sales SA |  | Not Started | Medium | 0% | Accountable: Pre-Sales Manager | Consulted: Infra/IT; Product Team; Informed: Sales; Project Manager; remaining specialists
53 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Confirm demo support resources and the support process. | Product Team | Product Team; Pre-Sales SA; Pre-Sales Manager |  | Not Started | Medium | 0% | Accountable: Pre-Sales Manager | Consulted: Infra/IT; Managed Service & Support; Project Manager; Informed: Sales; Delivery SA; Enterprise Architect (EA); remaining specialists
54 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Hold the demo or POC. | Pre-Sales SA | Pre-Sales SA |  | Not Started | Medium | 0% | Accountable: Pre-Sales Manager | Consulted: Sales; Product Team; Delivery SA; Infra/IT; Informed: Project Manager; Enterprise Architect (EA); remaining specialists
55 | Process Activity | 6.4 Shape Solution, Delivery, Estimates and Demo | Close the demo request and record evidence and follow-up actions. | Pre-Sales SA | Pre-Sales SA |  | Not Started | Medium | 0% | Accountable: Pre-Sales Manager | Consulted: Product Team; Project Manager; Infra/IT; Informed: Sales; Delivery SA; Enterprise Architect (EA); remaining specialists

## RAID
Type | Severity | Probability | Owner | Mitigating Action | Status

## Key Links
Document Name | Link
Customer RFx instructions and source documents
RFP Response Process Full RACI v4
Opportunity Teams / SharePoint workspace
WBS and proposal timeline
Clarification Q&A log
Compliance response workbook(s)
Proposal response master template
Solution architecture and integration diagrams
Estimate workbook and assumptions
Licence and maintenance cost model
RAID log
Demo / POC plan, script and evidence
Service Delivery Review pack
Bid Review pack and approvals
Final proposal submission folder
Submission evidence and customer acknowledgement
Proposal follow-up / defence folder
Retrospective and reusable assets library