## Slide 1
Vodaria Group · Converged BSS Transformation
RFx response kick-off pack
Reusable baseline for cross-functional RFx mobilisation
Purpose: align scope, ownership, decisions, evidence and review gates before response work accelerates.
Internal template | October 2026
Vodaria Group — Converged BSS Transformation (RFP OPP-24-0981)

## Slide 2
Kick-off outcomes
The meeting is complete when the wider team understands the bid and accepts how the response will be run.
1
Shared context
Why the customer is buying and what the programme must change
2
Scope baseline
In scope, out of scope, dependencies and open questions
3
Solution direction
A testable hypothesis, not a premature commitment
4
Mobilised team
Functions, owners, escalation paths and decision rights
5
Controlled plan
WBS, dates, review gates, evidence and working practices

## Slide 3
Customer context and opportunity
Vodaria Group, a tier-1 converged operator, has issued an RFP to replace fragmented legacy BSS with a single cloud-native create–sell–deliver platform across B2C and B2B.
Business context
Tier-1 converged operator: fixed, mobile and enterprise across 6 EU markets, ~28M subscribers Group strategy targets B2B growth and 5G SA monetisation by 2028 Six product catalogues, manual quote-to-order and 10-day tariff launches
Transformation intent
Single catalogue-driven lead-to-cash model across B2C, B2B and converged Zero-touch order flow-through above 90%; tariff launch in under 5 days Retain Salesforce CRM and SAP ERP; replace legacy CPQ, order management, charging and billing
What this means for the response
Faster time-to-market, lower cost-to-serve, converged customer experience Proven tier-1 delivery with a phased, low-risk migration EU sovereign hosting and certified TM Forum Open APIs are mandatory
Vodaria Group — Converged BSS Transformation (RFP OPP-24-0981)

## Slide 4
Scope baseline
The kick-off should make the response boundary visible before detailed ownership and estimation begin.
IN SCOPE
Product Catalog (B2C, B2B, converged) Configure Price Quote (CPQ) Order Management & decomposition Converged online charging (5G SA CHF) Convergent billing Operational visibility & fallout management TMF Open API integration, migration, testing and managed service
BOUNDARY / DEPENDENCY
Salesforce CRM (customer system of record) SAP ERP finance programme Network inventory (Vodaria NetCracker instance) Payment gateway and print-stream partner (AFP) AI root-cause roadmap item (2027) — subject to Product approval
NOT ASSUMED
CRM replacement Network provisioning / activation Mainframe AFP print generation (partner-led) Data cleansing of legacy source systems Hardware procurement

## Slide 5
Solution hypothesis
Hansen Catalog, CPQ, Order Management and Charging form a single cloud-native BSS core, integrated with Vodaria's retained Salesforce CRM via TMF Open APIs and events.
Salesforce CRM
Hansen CPQ
Commercial approval
Hansen Order Management
Portfolio & visibility
SAP ERP · Network inventory · Payments
Governed product, pricing, compatibility, dependency and decomposition logic
API-first integration
Event-enabled
Cloud-native
Outcome-led
Evidence-based

## Slide 6
Assumptions and validation priorities
Assumptions are working controls. Each needs an owner, evidence source and resolution date in the WBS/RAID.
Theme | Working assumption | Validation owner
CRM & integration | Salesforce remains system of record; integrate via TMF620/648/622 APIs. | EA / CPQ
Adjacent platforms | SAP ERP and network inventory interfaces owned by Vodaria IT; availability to confirm. | EA / Delivery
Scope maturity | 8-week discovery, then fixed-scope phases with joint change board. | PM / Sales
Hosting & support | EU sovereign cloud (Frankfurt), 4 environments, 24x7 L2/L3 support. | Infra / Support
AI / MCP | MCP interface for AI agents; AI root-cause is roadmap (2027). | Product / Security
Testing | Hansen SIT; Vodaria UAT with masked production data and named approvers. | Delivery / Customer
Kick-off action: confirm which assumptions must be validated before solution baseline, estimate lock or bid approval.

## Slide 7
Impacted functions and engagement model
Bring functions in at the point where their decision or evidence changes the response, not only at final review.
Sales
Customer strategy, win themes, commercials
Pre-Sales
Governance, solution, response quality
Project Management
WBS, RAID, estimates, delivery review
Product
Capability evidence, gaps and roadmap
Enterprise Architecture
Boundaries, integration and NFRs
Delivery SMEs
Implementation, migration and operations
Security & Privacy
Security directives, assurance evidence
Infrastructure / SaaS
Environments, sizing, service model
Managed Support
Coverage, L1-L3 boundary, SLAs
Commercial & Finance
Price model, approval and assumptions
Legal
Terms, disclaimers and exceptions
Training / Adoption
Enablement and transition approach

## Slide 8
Worked example timeline
Populate the live procurement milestones and internal gates during mobilisation.
02 Oct 2026
RFx issued
10 Oct 2026
Internal kick-off
28 Oct 2026
Clarification deadline
06 Nov 2026
Target content complete
10 Nov 2026
Proposal review
13 Nov 2026
Submission deadline
11 Nov 2026
Bid / cost reviews
02 Dec 2026
Evaluation milestone
Planning rule: work backwards from submission. Lock gates first, then reviews, authoring, estimation, clarification and mobilisation.

## Slide 9
Review gates and evidence
A gate is a decision supported by evidence, not simply a meeting in the diary.
G0
Mobilised
Team, workspace, WBS, RAID, cadence
G1
Requirements understood
Allocated sources, questions, scope and assumptions
G2
Solution baseline
Architecture, delivery, demo, estimate and dependencies
G3
Content complete
Proposal, workbook, annexes, evidence, costs
G4
Bid approved
Delivery, legal, security, commercial and executive conditions
G5
Submitted
Quality check, controlled issue and acknowledgement
G6
Closed
Follow-up, outcome, retrospective and archive

## Slide 10
Working practices
The kick-off should end with explicit team behaviours and immediate actions.
Control
One controlled workspace and latest-version links
Customer templates and structures preserved
Decisions, assumptions and changes recorded
Evidence linked to each claim and compliance answer
No uncontrolled placeholders at content complete
Collaboration
Named owners and backups
Short regular progress cadence
Escalate blockers early through agreed paths
Cross-functional reviews before final assurance
Use customer terminology and outcome-led narrative
Kick-off actions
Confirm initial scope and solution hypothesis Confirm function leads and WBS ownership Validate milestone and gate dates Assign assumptions and clarification questions Confirm next cadence and first deliverables
Definition of success: one team, one plan, one evidence-backed response baseline.